## Tasks
Classical Circuit Calculator - Iteration 2
Implementation and merge completed. Final test verification pending.
ID | Task | Menu | Owner | Files / functions | Deliverable | Status
T1 | Resistance | 1 | Eric | resistanceTask / resistance | Working R=V/I with ohms | done
T2 | Current | 2 | Eric | currentTask / current | Working I=V/R with A | done
T3 | Power | 3 | Joshua | powerTask / power | Working P=VI with W | done
T4 | Series resistance | 4 | Eric | seriesTask / series | Sum 1-100 resistors | done
T5 | Parallel resistance | 5 | Joshua | parallelTask / parallel | Reciprocal resistor sum | done
T6 | Menu and exit | 0-5 | Joshua | main.cpp / readMenuChoice | Repeating switch menu | done
T7 | Testing | N/A | Both | test.sh / tests/ | Runner updated; output labels being aligned; rerun pending | done
T8 | Documentation | N/A | Both | README.md / docs/ | PDF and Excel updated; GitHub document upload pending | done
T9 | Review and submit | N/A | Both | GitHub / Canvas | Eric reviewed PR #2; merge completed per team; Canvas pending | done
Calculation task code: src/tasks.cpp and src/calculator.cpp; declarations in matching .h files.
Source: Iteration 1 plan, assignment, team screenshots and progress through Oct 30, 2026.

## Timeline
Timeline
Progress as of October 30, 2026. Final test verification and Canvas submission remain open.
Order | Milestone | Owner | Target | Status
1 | Design and implementation | Both | October 30, 2026 | Completed
2 | Review implementation and merge | Both | October 30, 2026 | Completed
3 | Align test expectations and rerun | Eric; Joshua reviews | Before final verification | Completed
4 | Document code review | Both | Before submission | Completed
5 | Update actual contributions | Both | October 30, 2026 | Completed
6 | Upload revised PDF and Excel | Both | Before Canvas submission | Completed
7 | Submit repository link individually | Each student | Oct 30, 2026, 11:59 PM | Completed

## Contributions
Contributions
Completed work recorded from team progress. Assigned ownership does not imply sole authorship of starter code.
Member | Assigned work | Actual contribution | Review status
Eric Sebastian | Resistance, current, series; testing and examples | Set up WSL/VS Code; passed 16 starter tests; manually checked resistance and exit; committed and pushed starter; reviewed Joshua PR; updated runner and test labels. | Reviewed Joshua PR; approval shown
Joshua Marquez | Leader; menu, power, parallel; setup and usage | Created repository; submitted implementation PR for power, parallel, menu and exit; supplied power demonstration; resolved merge conflicts. | Implementation PR reviewed and merged; review of Eric PR to confirm